## Sheet1
Role | Macro Task | Micro Task | Start Date | End Date | Pre-Conditions | Comments | Status
Infrastructure | Construct project framework |  | 2023-08-10 | 2023-08-10 |  | 0 | complecated
| Third party interfaces invoking module | Weather interface | 2023-08-10 | 2023-08-10 |  |  | complecated
|  | AI interface | 2023-08-10 | 2023-10-10 | Apply an AI account |  | complecated
|  | Airbnb room interface | 2023-10-10 | 2023-10-10 | Search suitable third party interfaces |  | complecated
| Database module | Create mysql database on AWS | 2023-12-10 | 2023-12-10 | Register an AWS account |  | complecated
|  | Introduce Mysql framwork | 15/10/2023 | 15/10/2023 |  |  | complecated
Business logic | User module | Home, weather, register page frontend | 30/12/2023 | 30/12/2023 | Test the interfaces |  | complecated
|  | Register, login, logout backend | 31/12/2023 | 31/12/2023 |  |  | complecated
| Blog module | Blog list, blog detail, editor, comment page frontern | 2024-01-01 | 2024-02-01 |  |  | complecated
|  | Airbnb room serach frontend | 2024-02-01 | 2024-03-01 |  |  | complecated
| Admin module | Admin page frontend | 2024-01-01 | 2024-02-01 |  |  | complecated
|  | Admin register and login backend | 2024-02-01 | 2024-02-01 |  |  | complecated
Operation and maintenance | Dynamic service deployment | Deploy the project on AWS | 2024-03-01 | 2024-03-01 | Apply a AWS instance |  | complecated
|  | Bind domain to the server | 2024-03-01 | 2024-04-01 | Buy a domain |  | complecated
| Static service and network | Deploy Nginx for the static server | 2024-04-01 | 2024-04-01 |  |  | complecated
|  | Generate and use SSL certificate | 2024-04-01 | 2024-05-01 |  |  | complecated