## Sheet1
Role | Macro Task | Micro Task | Start Date | End Date | Pre-Conditions | Comments | Status
Infrastructure | Construct project frame |  | 2023-08-10 | 2023-08-10 |  |  | completed
| Third party interfaces invoking module | Weather interface | 2023-08-10 | 2023-08-10 |  | Permite broswer to get latitude and longitude | completed
|  | AI interface | 2023-08-10 | 2023-10-10 | Apply an AI account |  | completed
|  | Airbnb room interface | 2023-10-10 | 2023-10-10 | Search suitable third party interfaces |  | completed
| Database module | Create mysql database on AWS | 2023-12-10 | 2023-12-10 | Register an AWS account |  | completed
|  | Introduce Mybatis framwork | 15/10/2023 | 15/10/2023 |  |  | completed
Business logic | User module | Home page frontend | 28/12/2023 | 28/12/2023 |  |  | completed
|  | Show weather information | 29/12/2023 | 29/12/2023 |  |  | completed
|  | Register page frontend | 30/12/2023 | 30/12/2023 | Test the interfaces |  | completed
|  | Register process backend | 31/12/2023 | 31/12/2023 |  |  | completed
|  | Login process backend | 31/12/2023 | 31/12/2023 |  |  | completed
|  | Logout process backend | 31/12/2023 | 31/12/2023 |  |  | completed
| Blog module | Blog list page frontend | 2024-01-01 | 2024-01-01 |  |  | completed
|  | Blog detail frontend | 2024-01-01 | 2024-01-01 |  |  | completed
|  | Editor detail frontend | 2024-02-01 | 2024-02-01 |  |  | completed
|  | Comment page frontern | 2024-02-01 | 2024-02-01 |  |  | completed
|  | Airbnb room serach frontend | 2024-02-01 | 2024-02-01 |  |  | completed
| Admin module | Admin page frontend | 2024-03-01 | 2024-03-01 |  |  | completed
|  | Admin register and login backend | 2024-03-01 | 2024-03-01 |  |  | completed
Operation and maintenance | Dynamic service deployment | Deploy the project on AWS | 2024-04-01 | 2024-04-01 | Apply a AWS instance | Install sdkman to simplize the process | completed
|  | Bind domain to the server | 2024-04-01 | 2024-04-01 | Buy a domain |  | completed
| Static service and network | Deploy Nginx for the static server | 2024-05-01 | 2024-05-01 |  | Listening to the port 443 and 80, transfor request to port 8080 | completed
|  | Generate and use SSL certificate | 2024-06-01 | 2024-06-01 |  | Generate a free SSL certificate by Certbot | completed